## Sheet1
IHTM New Project Query Monitoring Sheets - GouGouchi & External
SL | Details |  |  |  | Stages | Date | Remarks | Plant | 2026-01-01 | [30 empty] | 2026-02-01 | [27 empty] | 2026-03-01
|  |  | Process | Trigger Resp.
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Project name | TRAINING SETUP CONVEYOR | Date Of Query | Customer | Query | 2025-06-19 |  | P2 PAINT IT-1514
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-10-21
| Customer name | SWAMY | Concept | IHTM | Concept | 2025-11-11
| Plant Details | P2 TOP COAT | Estimation | IHTM | Estimation
| IHTM Leader | D V RAJESH | PO / Budget transfer | Customer | PO/Budget
2 | Project name | IP Manipulator | Date Of Query | Customer | Query | 2025-08-04 |  | P1 ASSY IT-1505
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-19
| Customer name | Shashank | Concept | IHTM | Concept
| Plant Details | P1 Assy | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
3 | Project name | SM GBL SCA & SRA ECI additonal items | Date Of Query | Customer | Query |  |  | P3 GBL
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Rahul R | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation | 2025-12-12
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
4 | Project name | Smart flow rack | Date Of Query | Customer | Query | 2025-11-06 |  | P1 ASSY IT-1517
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | suresh a p | Concept | IHTM | Concept | 2026-01-02
| Plant Details | p1 assy | Estimation | IHTM | Estimation
| IHTM Leader | d v rajesh | PO / Budget transfer | Customer | PO/Budget
5 | Project name | 737D BD Inner nut weld | Date Of Query | Customer | Query | 2025-11-19 |  | P3 WELD IT-1429
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-21
| Customer name | A V Raghvendra | Concept | IHTM | Concept
| Plant Details | P1 WELD | Estimation | IHTM | Estimation | 2026-01-08
| IHTM Leader | PAVAN | PO / Budget transfer | Customer | PO/Budget
6 | Project name | Smart flow rack | Date Of Query | Customer | Query | 2025-10-08 |  | P2 ASSY IT-1533
|  |  | Spec discussion | Customer/IHTM | Spec | 24-10-12025
| Customer name | shashank | Concept | IHTM | Concept | 2025-11-21
| Plant Details | P2 Assy | Estimation | IHTM | Estimation
| IHTM Leader | D V RAJESH | PO / Budget transfer | Customer | PO/Budget
7 | Project name | FPS Free pass station | Date Of Query | Customer | Query | 2025-10-10 |  | P2 PRESS IT-1554
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-06
| Customer name | AMIT | Concept | IHTM | Concept
| Plant Details | P2 PRESS | Estimation | IHTM | Estimation
| IHTM Leader | RAJESH | PO / Budget transfer | Customer | PO/Budget
8 | Project name | Stud cell to UB GBL Transfer system |  |  | Query | 2025-12-15 |  | P2 WELD IT-1546
Spec
| Customer name | umesh mg |  |  | Concept | 2026-01-08
| Plant Details | P2 Weld |  |  | Estimation
| IHTM Leader | Pavan |  |  | PO/Budget
9 | Project name | 619D Lexus Exhaust lifter | Date Of Query | Customer | Query | 2025-12-15 |  | LEXUS IT-1552
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-18
| Customer name | swastik | Concept | IHTM | Concept
| Plant Details | camry | Estimation | IHTM | Estimation | 2025-12-30
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
10 | Project name | UBC Application | Date Of Query | Customer | Query | 2025-12-16 |  | P2 PAINT IT-1555
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-24
| Customer name | Jagadesh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
11 | Project name | Offline area Automation | Date Of Query | Customer | Query | 2025-10-18 |  | P2 PAINT IT-1529
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-14
| Customer name | adarsh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| IHTM Leader | D V rajesh | PO / Budget transfer | Customer | PO/Budget
12 | Project name | Bumper setup for P3 |  |  | Query | 2025-11-13 |  | P3 ASSY IT-1539
[5 empty] | Spec | 2025-12-19
| Customer name | Suresh AP |  |  | Concept
| Plant Details | P3 |  |  | Estimation
| IHTM Leader | D V Rajesh |  |  | PO/Budget
13 | Project name | Smart flow rack |  |  | Query | 2025-12-05 |  | P2 PRESS IT-1542
[5 empty] | Spec | 2025-12-16
| Customer name | amruth |  |  | Concept
| Plant Details | P2 Press |  |  | Estimation
| IHTM Leader | D V Rajesh |  |  | PO/Budget
14 | Project name | PPO Pitch lifter pick andn place |  |  | Query | 2026-01-12 |  | PPO IT-1561
Spec
| Customer name | Vishal |  |  | Concept
| Plant Details | PPO |  |  | Estimation
| IHTM Leader | Pavan |  |  | PO/Budget
15 | Project name | ILCD Automation cell required |  |  | Query | 2026-01-17 |  | P2 ILCD IT-1562
Spec
| Customer name | anil |  |  | Concept
| Plant Details | ILCD |  |  | Estimation
| IHTM Leader | DV Rajesh |  |  | PO/Budget
16 | Project name | Dash Sealer Autosealer | Date Of Query | Customer | Query | 2026-01-08 |  | P3 WELD IT-1566
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh MG | Concept | IHTM | Concept
| Plant Details | P3 WELD | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
17 | Project name | Dolly for NPC | Date Of Query | Customer | Query | 2026-01-09 |  | NPC IT-1557
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-12
| Customer name | Nischitha | Concept | IHTM | Concept
| Plant Details | NPC | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
18 | Project name | SM GBL PIERCING HOLE CHANGE POINT_ ECI | Date Of Query | Customer | Query | 2026-01-02 |  | P3 GBL IT-1000.1
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-10
| Customer name | Rahul | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
19 | Project name | SRA Gripper ECI parts | Date Of Query | Customer | Query | 2026-01-09 |  | P3 GBL IT-1009.1
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-17
| Customer name | Rahul | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
20 | Project name | Engine line tray ( Safety Improvement Concept ) | Date Of Query | Customer | Query | 2026-01-17 |  | P1 ASSY IT-0831.1
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | pramod | Concept | IHTM | Concept
| Plant Details | P1 Assy | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
21 | Project name | Oyoko dolly | Date Of Query | Customer | Query | 2025-12-05 |  | ILCD IT-1563
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-14
| Customer name | Vineet | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
22 | Project name | Truck Vehicle Development | Date Of Query | Customer | Query | 2025-12-05 |  | ILCD IT-1540
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-17
| Customer name | Vineet | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
23 | Project name | Oven Elimination | Date Of Query | Customer | Query | 2025-12-15 |  | P2 PAINT IT-1564
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Adarsh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
24 | Project name | MRA & MCA | Date Of Query | Customer | Query |  |  | P3 WELD IT-1466
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh mg | Concept | IHTM | Concept
| Plant Details | P3 WELD | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
25 | Project name | GF Dyso auto Loading from truck | Date Of Query | Customer | Query |  |  | GF P4 IT-1565
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | vinod | Concept | IHTM | Concept
| Plant Details | GF | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
26 | Project name | Safety Dojo | Date Of Query | Customer | Query | 2025-12-26 |  | NMEC IT-1558
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-07
| Customer name | Vinod | Concept | IHTM | Concept
| Plant Details | NMEC | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
27 | Project name | U/B Transfer system | Date Of Query | Customer | Query |  |  | P3 WELD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh ng | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
28 | Project name | Empty sorting dolly | Date Of Query | Customer | Query | 2026-01-19 |  | P2 ILCD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | C M Srinivas | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
29 | Project name | U/B Dolly Transfer system | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | umesh n g | Concept | IHTM | Concept
| Plant Details | weld p2 | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
30 | Project name | Back door ASP Robo Cell | Date Of Query | Customer | Query |  |  | IT-1570 P3 WELD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Tejaswi bhat | Concept | IHTM | Concept
| Plant Details | p2 weld | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
31 | Project name | Robot Angle Measurement Tool | Date Of Query | Customer | Query | 2026-01-28 |  | IT-1567 P2 WELD SEIBI
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Yashwant | Concept | IHTM | Concept
| Plant Details | P2 WELD SEIBI | Estimation | IHTM | Estimation | 2026-01-29 | bar: 29
| IHTM Leader | PAVAN | PO / Budget transfer | Customer | PO/Budget
32 | Project name | Old AGV Elimination | Date Of Query | Customer | Query | 2026-01-29 |  | IT-1569 P2 WELD
|  |  | Spec discussion | Customer/IHTM | Spec | bar: 3
| Customer name | P2 WELD | Concept | IHTM | Concept
| Plant Details | DIPIN | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
33 | Project name | Training Area Setup | Date Of Query | Customer | Query | 2026-01-28 |  | IT-1571 P1 ASSY
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-29
| Customer name | Pavaman | Concept | IHTM | Concept
| Plant Details | P1 Assy | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
34 | Project name | REBORN JIG 737D | Date Of Query | Customer | Query | 2026-01-13 |  | IT-1560 P3 WELD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | SRIVATSA | Concept | IHTM | Concept
| Plant Details | P3 WELD | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
35 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
36 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
37 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
38 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
39 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
40 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
41 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
42 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
43 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
44 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
45 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
46 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
47 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
48 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
49 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
50 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
51 | Project name |  | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name |  | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget