## Sheet1
SL No | Project name | Tool No | Customer Name | Plant Details | IHTM Leader | Current Stage | Query date | Spec date | Concept Date | Estimation date | PO date
1 | TRAINING SETUP CONVEYOR | IT-1514 | Swamy | P1 Assy | John | Estimation | 19-06-2025 | 21-06-2025 | 11-11-2025 | 15-12-2025
2 | IP Manipulator | IT-1515 | Shashank | P2 Top coat | Joe | Spec | 20-06-2025 | 22-06-2025
3 | SM GBL SCA & SRA ECI additional items | IT-1516 | Shashank | P3 GBL | Dane | Spec | 21-06-2025 | 23-06-2025
4 | Smart flow rack | IT-1517 | Shashank | P1 Assy | John | Spec | 22-06-2025 | 24-06-2025
5 | 737D BD Inner nut weld | IT-1518 | Suresh | P1 Weld | Joe | Concept | 23-06-2025 | 25-06-2025 | 10-09-2025
6 | Smart flow rack | IT-1519 | Amit | P2 Top coat | Dane | Spec | 24-06-2025 | 26-06-2025
7 | FPS Free pass station | IT-1520 | Adarsh | P3 GBL | John | Query | 27-06-2025
8 | Stud cell to UB GBL Transfer system | IT-1521 | Jagadeesh | P1 Assy | Joe | Estimation | 01-07-2025 | 15-07-2025 | 10-08-2025 | 20-09-2025
9 | 619D Lexus Exhaust lifter | IT-1522 | Anil | P1 Weld | Dane | PO | 05-06-2025 | 20-06-2025 | 10-07-2025 | 25-07-2025 | 15-08-2025
10 | UBC Application | IT-1523 | Nischitha | P2 Top coat | John | PO | 03-06-2025 | 18-06-2025 | 08-07-2025 | 22-07-2025 | 10-08-2025
11 | Offline area Automation | IT-1524 | Swamy | P3 GBL | Dane | Concept | 10-07-2025 | 25-07-2025 | 05-09-2025
12 | Bumper setup for P3 | IT-1525 | Suresh | P3 GBL | John | Spec | 12-07-2025 | 28-07-2025
13 | Smart flow rack | IT-1526 | Amit | P1 Assy | Joe | Query | 15-07-2025
14 | PPO Pitch lifter pick and place | IT-1527 | Adarsh | P2 Top coat | Dane | Estimation | 01-07-2025 | 16-07-2025 | 05-08-2025 | 01-10-2025
15 | ILCD Automation cell required | IT-1528 | Jagadeesh | P1 Weld | John | Spec | 18-07-2025 | 02-08-2025
16 | Dash Sealer Autosealer | IT-1529 | Anil | P2 Top coat | Joe | PO | 20-06-2025 | 05-07-2025 | 25-07-2025 | 10-08-2025 | 01-09-2025
17 | Dolly for NPC | IT-1530 | Nischitha | P3 GBL | Dane | Concept | 22-07-2025 | 06-08-2025 | 20-09-2025
18 | SM GBL PIERCING HOLE CHANGE POINT ECI | IT-1531 | Shashank | P1 Assy | John | Query | 25-07-2025
19 | SRA Gripper ECI parts | IT-1532 | Suresh | P2 Top coat | Joe | Spec | 28-07-2025 | 12-08-2025
20 | Engine line tray Safety Improvement Concept | IT-1533 | Amit | P1 Weld | Dane | Estimation | 01-08-2025 | 16-08-2025 | 05-09-2025 | 20-10-2025
21 | Oyoko dolly | IT-1534 | Adarsh | P3 GBL | John | Concept | 05-08-2025 | 20-08-2025 | 10-10-2025
22 | Truck Vehicle Development | IT-1535 | Jagadeesh | P1 Assy | Joe | PO | 10-07-2025 | 25-07-2025 | 15-08-2025 | 01-09-2025 | 20-09-2025
23 | Oven Elimination | IT-1536 | Anil | P2 Top coat | Dane | Spec | 08-08-2025 | 23-08-2025
24 | MRA & MCA | IT-1537 | Nischitha | P1 Weld | John | Estimation | 10-08-2025 | 25-08-2025 | 15-09-2025 | 30-10-2025
25 | GF Dyso auto Loading from truck | IT-1538 | Swamy | P3 GBL | Joe | Query | 12-08-2025
26 | Safety Dojo | IT-1539 | Suresh | P1 Assy | Dane | Concept | 15-08-2025 | 30-08-2025 | 20-10-2025
27 | U/B Transfer system | IT-1540 | Amit | P2 Top coat | John | PO | 18-07-2025 | 02-08-2025 | 22-08-2025 | 07-09-2025 | 25-09-2025
28 | Empty sorting dolly | IT-1541 | Adarsh | P1 Weld | Joe | Spec | 20-08-2025 | 04-09-2025
29 | U/B Dolly Transfer system | IT-1542 | Jagadeesh | P3 GBL | Dane | Estimation | 22-08-2025 | 06-09-2025 | 26-09-2025 | 10-11-2025
30 | Back door ASP Robo Cell | IT-1543 | Anil | P2 Weld | John | Concept | 25-08-2025 | 09-09-2025 | 30-10-2025
31 | Robot Angle Measurement Tool | IT-1544 | Yashwant | P2 Weld SEIBI | Pavan | Query | 28-01-2026
32 | Old AGV Elimination | IT-1545 | Dipin | P2 Weld | Pavan | Query | 29-01-2026
33
34

## Sheet7
SL | Details |  |  |  | Stages | Date | Remarks | Plant
|  |  | Process | Trigger Resp.
1 | Project name | TRAINING SETUP CONVEYOR | Date Of Query | Customer | Query | 2025-06-19 | Estimation | P2 PAINT IT-1514
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-10-21
| Customer name | SWAMY | Concept | IHTM | Concept | 2025-11-11
| Plant Details | P2 TOP COAT | Estimation | IHTM | Estimation
| IHTM Leader | D V RAJESH | PO / Budget transfer | Customer | PO/Budget
2 | Project name | IP Manipulator | Date Of Query | Customer | Query | 2025-08-04 | Spec | P1 ASSY IT-1505
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-19
| Customer name | Shashank | Concept | IHTM | Concept
| Plant Details | P1 Assy | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
3 | Project name | SM GBL SCA & SRA ECI additonal items | Date Of Query | Customer | Query |  | Estimation | P3 GBL
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Rahul R | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation | 2025-12-12
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
4 | Project name | Smart flow rack | Date Of Query | Customer | Query | 2025-11-06 | Concept | P1 ASSY IT-1517
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | suresh a p | Concept | IHTM | Concept | 2026-01-02
| Plant Details | p1 assy | Estimation | IHTM | Estimation
| IHTM Leader | d v rajesh | PO / Budget transfer | Customer | PO/Budget
5 | Project name | 737D BD Inner nut weld | Date Of Query | Customer | Query | 2025-11-19 | Estimation | P3 WELD IT-1429
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-21
| Customer name | A V Raghvendra | Concept | IHTM | Concept
| Plant Details | P1 WELD | Estimation | IHTM | Estimation | 2026-01-08
| IHTM Leader | PAVAN | PO / Budget transfer | Customer | PO/Budget
6 | Project name | Smart flow rack | Date Of Query | Customer | Query | 2025-10-08 | Estimation | P2 ASSY IT-1533
|  |  | Spec discussion | Customer/IHTM | Spec | 24-10-12025
| Customer name | shashank | Concept | IHTM | Concept | 2025-11-21
| Plant Details | P2 Assy | Estimation | IHTM | Estimation
| IHTM Leader | D V RAJESH | PO / Budget transfer | Customer | PO/Budget
7 | Project name | FPS Free pass station | Date Of Query | Customer | Query | 2025-10-10 | Spec | P2 PRESS IT-1554
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-06
| Customer name | AMIT | Concept | IHTM | Concept
| Plant Details | P2 PRESS | Estimation | IHTM | Estimation
| IHTM Leader | RAJESH | PO / Budget transfer | Customer | PO/Budget
8 | Project name | Stud cell to UB GBL Transfer system |  |  | Query | 2025-12-15 | Estimation | P2 WELD IT-1546
Spec
| Customer name | umesh mg |  |  | Concept | 2026-01-08
| Plant Details | P2 Weld |  |  | Estimation
| IHTM Leader | Pavan |  |  | PO/Budget
9 | Project name | 619D Lexus Exhaust lifter | Date Of Query | Customer | Query | 2025-12-15 | Estimation | LEXUS IT-1552
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-18
| Customer name | swastik | Concept | IHTM | Concept
| Plant Details | camry | Estimation | IHTM | Estimation | 2025-12-30
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
10 | Project name | UBC Application | Date Of Query | Customer | Query | 2025-12-16 | Spec | P2 PAINT IT-1555
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-24
| Customer name | Jagadesh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
11 | Project name | Offline area Automation | Date Of Query | Customer | Query | 2025-10-18 | Spec | P2 PAINT IT-1529
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-11-14
| Customer name | adarsh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| IHTM Leader | D V rajesh | PO / Budget transfer | Customer | PO/Budget
12 | Project name | Bumper setup for P3 |  |  | Query | 2025-11-13 | Spec | P3 ASSY IT-1539
[5 empty] | Spec | 2025-12-19
| Customer name | Suresh AP |  |  | Concept
| Plant Details | P3 |  |  | Estimation
| IHTM Leader | D V Rajesh |  |  | PO/Budget
13 | Project name | Smart flow rack |  |  | Query | 2025-12-05 | Spec | P2 PRESS IT-1542
[5 empty] | Spec | 2025-12-16
| Customer name | amruth |  |  | Concept
| Plant Details | P2 Press |  |  | Estimation
| IHTM Leader | D V Rajesh |  |  | PO/Budget
14 | Project name | PPO Pitch lifter pick andn place |  |  | Query | 2026-01-12 | Query | PPO IT-1561
Spec
| Customer name | Vishal |  |  | Concept
| Plant Details | PPO |  |  | Estimation
| IHTM Leader | Pavan |  |  | PO/Budget
15 | Project name | ILCD Automation cell required |  |  | Query | 2026-01-17 | Query | P2 ILCD IT-1562
Spec
| Customer name | anil |  |  | Concept
| Plant Details | ILCD |  |  | Estimation
| IHTM Leader | DV Rajesh |  |  | PO/Budget
16 | Project name | Dash Sealer Autosealer | Date Of Query | Customer | Query | 2026-01-08 | Query | P3 WELD IT-1566
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh MG | Concept | IHTM | Concept
| Plant Details | P3 WELD | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
17 | Project name | Dolly for NPC | Date Of Query | Customer | Query | 2026-01-09 | Spec | NPC IT-1557
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-12
| Customer name | Nischitha | Concept | IHTM | Concept
| Plant Details | NPC | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
18 | Project name | SM GBL PIERCING HOLE CHANGE POINT_ ECI | Date Of Query | Customer | Query | 2026-01-02 | Spec | P3 GBL IT-1000.1
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-10
| Customer name | Rahul | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
19 | Project name | SRA Gripper ECI parts | Date Of Query | Customer | Query | 2026-01-09 | Spec | P3 GBL IT-1009.1
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-17
| Customer name | Rahul | Concept | IHTM | Concept
| Plant Details | P3 GBL | Estimation | IHTM | Estimation
| IHTM Leader | D V Rajesh | PO / Budget transfer | Customer | PO/Budget
20 | Project name | Engine line tray ( Safety Improvement Concept ) | Date Of Query | Customer | Query | 2026-01-17 | Query | P1 ASSY IT-0831.1
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | pramod | Concept | IHTM | Concept
| Plant Details | P1 Assy | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
21 | Project name | Oyoko dolly | Date Of Query | Customer | Query | 2025-12-05 | Spec | ILCD IT-1563
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-14
| Customer name | Vineet | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
22 | Project name | Truck Vehicle Development | Date Of Query | Customer | Query | 2025-12-05 | Spec | ILCD IT-1540
|  |  | Spec discussion | Customer/IHTM | Spec | 2025-12-17
| Customer name | Vineet | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
23 | Project name | Oven Elimination | Date Of Query | Customer | Query | 2025-12-15 | Query | P2 PAINT IT-1564
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Adarsh | Concept | IHTM | Concept
| Plant Details | P2 Paint | Estimation | IHTM | Estimation
| Designer PIC |  | PO / Budget transfer | Customer | PO/Budget
24 | Project name | MRA & MCA | Date Of Query | Customer | Query |  |  | P3 WELD IT-1466
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh mg | Concept | IHTM | Concept
| Plant Details | P3 WELD | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
25 | Project name | GF Dyso auto Loading from truck | Date Of Query | Customer | Query |  |  | GF P4 IT-1565
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | vinod | Concept | IHTM | Concept
| Plant Details | GF | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
26 | Project name | Safety Dojo | Date Of Query | Customer | Query | 2025-12-26 | Spec | NMEC IT-1558
|  |  | Spec discussion | Customer/IHTM | Spec | 2026-01-07
| Customer name | Vinod | Concept | IHTM | Concept
| Plant Details | NMEC | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
27 | Project name | U/B Transfer system | Date Of Query | Customer | Query |  |  | P3 WELD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Umesh ng | Concept | IHTM | Concept
| Plant Details |  | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
28 | Project name | Empty sorting dolly | Date Of Query | Customer | Query | 2026-01-19 | Query | P2 ILCD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | C M Srinivas | Concept | IHTM | Concept
| Plant Details | P2 ILCD | Estimation | IHTM | Estimation
| IHTM Leader |  | PO / Budget transfer | Customer | PO/Budget
29 | Project name | U/B Dolly Transfer system | Date Of Query | Customer | Query
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | umesh n g | Concept | IHTM | Concept
| Plant Details | weld p2 | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget
30 | Project name | Back door ASP Robo Cell | Date Of Query | Customer | Query |  |  | IT-1570 P3 WELD
|  |  | Spec discussion | Customer/IHTM | Spec
| Customer name | Tejaswi bhat | Concept | IHTM | Concept
| Plant Details | p2 weld | Estimation | IHTM | Estimation
| IHTM Leader | Pavan | PO / Budget transfer | Customer | PO/Budget